## HTML Screen Design Status
S.NO | Comp Name | Persona | XSL File Name | Modified by Matt | Resource | Start Date | End Date | Status | Comment
1 | Relus_125-Categories.jpg | Sponsor |  | No | Saurabh | 2015-01-14 | 2015-01-14 | Completed
2 | Relus_125-Claim-History.jpg | Sponsor |  | No | Saurabh | 2015-01-14 | 2015-01-14 | Completed
3 | Relus_125-Payments.jpg | Sponsor |  | No | Saurabh | 2015-01-14 | 2015-01-14 | Completed
4 | Relus_CSR-Personal-Profile.jpg | CSR |  | No | Saurabh |  |  | In Progress | Work in progress, waiting on Edmund to provide details for the bottom two sections
5 | Relus_PERSONAL-PROFILE-COLLAPSED.jpg | Participant |  | No | Edmund |  |  | Completed
6 | Relus_PERSONAL-PROFILE-EXPANDED.jpg | Participant |  | No | Edmund |  |  | Completed
7 | Relus_Plan-Selection_PARTICIPANT.jpg | Participant |  | No | Sasikanth K | 2015-01-14 | 2015-01-14 | Completed
8 | Relus_Plan-Selection_SPONSOR.jpg | Sponsor |  | No | Sasikanth K | 2015-01-14 | 2015-01-14 | Completed
9 | Relus_RATE-of-RETURN.jpg | Participant |  | No | Edmund |  |  | Completed
10 | Relus_SPONSOR-add-update.jpg | Sponsor |  | No | Edmund |  |  | Completed
11 | Relus_INVESTMENT-MODEL-REALIGNMENT.jpg | Advisor |  | No | Sasikanth K | 2015-02-03 | 2015-02-03 | Completed
12 | Relus_INVESTMENT-MODEL-REALIGNMENT-CONFIRMATION.jpg | Advisor |  | No | Sasikanth K | 2015-01-27 | 2015-01-27 | Completed
13 | Relus_INVESTMENT-MODEL-REALIGNMENT-FINISH.jpg | Advisor |  | No | Amit | 2015-01-27 | 2015-01-27 | Completed
14 | Relus_MODEL-FUND-TRANSFER-QUEUE.jpg | Advisor |  | No | Sasikanth K | 2015-01-27 | 2015-01-29 | Completed
15 | Relus_MODEL-FUND-TRANSFERS.jpg | Advisor |  | No | Amit | 2015-01-28 | 2015-01-28 | Completed
16 | Relus_MODEL-FUND-TRANSFERS-FINISH.jpg | Advisor |  | No | Amit | 2015-01-28 | 2015-02-03 | Completed
17 | Relus_MODEL-FUND-TRANSFERS-REVIEW.jpg | Advisor |  | No | Sasikanth K | 2015-01-28 | 2015-01-29 | Completed
18 | Relus_MODEL-PLAN-DETAILS.jpg | Advisor |  | No | Sasikanth K | 2015-01-30 | 2015-01-30 | Completed
19 | Relus_MODEL-SELECT.jpg | Advisor |  | No | Sasikanth K | 2015-01-30 | 2015-02-02 | Completed
20 | Relus_PARTICIPANT-DETAILS.jpg | Advisor |  | No | Sasikanth K | 2015-02-02 | 2015-02-02 | Completed
21 | Message-Dropdown.png | Header
22 | Relius_MESSAGING-1.jpg | Header
23 | Relius_MESSAGING-2.jpg | Header
24 | Relius_MESSAGING-3.jpg | Header
25 | Relius_MESSAGING-4.jpg | Header
Note on E2: If this column contains Yes, it indicates, Matt modified the comp after html was created of work had started.